## Sheet1
1105 Mass Ave Condo Assoc |  | version 21
Maintenance Schedule |  | 2023-12-14
Project Name | Priority | Description | SWAG cost | Finish by Date | Depends on Other Project? | Comments | Next Action | Whose Action? | Action Date | Capital Expense or Operating Budget? | Potential Vendors | Bid 1 | Bid 2 | Actual Cost
MWRA gas/oil separator | 1A | Evaluate existing system and design installation of an oil gas separator to handle floor drains and grates in garage | 200000 | December, 2014 or TBD by Board |  | Water test done by plumber to confirm garage drains go into sanitary lines | Waiting for engineer report and recommendations | Steve Forte | Engineer completed inspection, now waiting for report | Capital expense
Main hot water shut off to the building does not work | 4A | 3" ball valve does not work to hold hot water from leaving tanks - no hot water comes down | 5500 | November, 2019 |  |  | Schedule with plumber for after hours work | Mike to schedule overnight work with plumber |  | Capital expense
Hot water room 3" valve | B | Valve does not shut completely and allows air into the system. Last time hit valve and it might have fixed it | 5000 | 2018 |  |  | Schedule with plumber for after hours work | to schedule overnight work with plumber | 2018 | Capital expense
Concrete Façade | B | Fix discoloration where concrete has been patched | 10,000, ceiling alone was $5883, this needs hand painting | 2018 |  | Needs Board approval |  | Elder | Not yet approved, unknown | operating expense
Cold water shut off on the 4" main in the compactor room | C | Does not shut completely. This shuts the water from the lobby level up. So only 1st floor stores have water. Not urgent | 5000 |  |  |  | Schedule plumber for after hours work | to schedule overnight work with plumber | 2020 | Capital expense
Tile replacement | C | Replace tiles on the mezzanine level | $27,000 (from cap. Needs study) | May, 2020 | no | Difficulty in finding tile to fit the height of the existing tile. Need something that is non skid. Made contact with manufacturer in Germany, but tile size is much larger. | Select possible replacement tiles | Elder and Myra | Not specified | Capital expense
Hallway HVAC unit | C | Repair hallway air system that puts heated air into the hallways |  | Summer, 2020 | no | Working on getting new smoke detector stop switch